## ganttChart
Task | Days Since Start | Days Left for Completion | Day end | T | 2024-08-27 | 1 | Start | End | BackEnd
Team Composition Form | 0 | 4 | 4 | W | 2024-08-28 | 2 | 2024-09-16 | 2024-09-30 | Table Design
Project Overview Proposal | 4 | 7 | 11 | Th | 2024-08-29 | 3 | 2024-09-30 | 2024-10-13 | Crud
Software Development Plan | 11 | 7 | 18 | F | 2024-08-30 | 4 | 2024-10-13 | 2024-10-28 | Business Logic
User Story Compendium | 18 | 7 | 25 | Sa | 2024-08-31 | 5 | 2024-10-28 | 2024-11-04 | Reports
MVS | 25 | 2 | 27 | Su | 2024-09-01 | 6 |  |  | Testing
Requirements Specification | 27 | 5 | 32 | M | 2024-09-02 | 7 | Start | End | Front End
Wireframe | 27 | 7 | 34 | T | 2024-09-03 | 8 | 2024-09-22 | 2024-09-29 | Wireframes
Table Design | 21 | 14 | 35 | W | 2024-09-04 | 9 | 2024-09-29 | 2024-10-06 | UI
Design Specificaition | 32 | 14 | 46 | Th | 2024-09-05 | 10 | 2024-10-14 | 2024-10-28 | HTML/CSS
CRUD operations | 35 | 14 | 49 | F | 2024-09-06 | 11 | 2024-10-28 | 2024-11-04 | Reports
UI Tasks Complete | 34 | 14 | 48 | Sa | 2024-09-07 | 12 |  |  | Testing
Business Logic / Code complete | 49 | 14 | 63 | Su | 2024-09-08 | 13
HTML / CSS - Finailzed | 49 | 14 | 63 | M | 2024-09-09 | 14
Reports - integrate for reports | 63 | 7 | 70 | T | 2024-09-10 | 15
Additional Features as time allows | 70 | 7 | 77 | W | 2024-09-11 | 16
Testing / Finalizing | 77 | 14 | 91 | Th | 2024-09-12 | 17
|  |  |  | F | 2024-09-13 | 18
|  |  |  | Sa | 2024-09-14 | 19
Task | Days Since Start | Days Left for Completion | Day end | Su | 2024-09-15 | 20
Team Composition Form | 0 | 1 | 1 | M | 2024-09-16 | 21
Project Overview Proposal | 1 | 1 | 2 | T | 2024-09-17 | 22
Software Development Plan | 2 | 1 | 3 | W | 2024-09-18 | 23
User Story Compendium | 3 | 1 | 4 | Th | 2024-09-19 | 24
MVS | 4 | 1 | 4 | F | 2024-09-20 | 25
Requirements Specification | 4 | 1 | 5 | Sa | 2024-09-21 | 26
Wireframe | 4 | 1 | 5 | Su | 2024-09-22 | 27
Table Design | 3 | 2 | 5 | M | 2024-09-23 | 28
Design Specificaition | 5 | 2 | 7 | T | 2024-09-24 | 29
CRUD operations | 5 | 2 | 7 | W | 2024-09-25 | 30
UI Tasks Complete | 5 | 2 | 7 | Th | 2024-09-26 | 31
Business Logic / Code complete | 7 | 2 | 9 | F | 2024-09-27 | 32
HTML / CSS - Finailzed | 7 | 2 | 9 | Sa | 2024-09-28 | 33
Reports - integrate for reports | 9 | 1 | 10 | Su | 2024-09-29 | 34
Additional Features as time allows | 10 | 1 | 11 | M | 2024-09-30 | 35
Testing / Finalizing | 11 | 2 | 13 | T | 2024-10-01 | 36
|  |  |  | W | 2024-10-02 | 37
|  |  |  | Th | 2024-10-03 | 38
|  |  |  | F | 2024-10-04 | 39
|  |  |  | Sa | 2024-10-05 | 40
|  |  |  | Su | 2024-10-06 | 41
|  |  |  | M | 2024-10-07 | 42
|  |  |  | T | 2024-10-08 | 43
|  |  |  | W | 2024-10-09 | 44
|  |  |  | Th | 2024-10-10 | 45
|  |  |  | F | 2024-10-11 | 46
|  |  |  | Sa | 2024-10-12 | 47
|  |  |  | Su | 2024-10-13 | 48
|  |  |  | M | 2024-10-14 | 49
|  |  |  | T | 2024-10-15 | 50
|  |  |  | W | 2024-10-16 | 51
|  |  |  | Th | 2024-10-17 | 52
|  |  |  | F | 2024-10-18 | 53
|  |  |  | Sa | 2024-10-19 | 54
|  |  |  | Su | 2024-10-20 | 55
|  |  |  | M | 2024-10-21 | 56
|  |  |  | T | 2024-10-22 | 57
|  |  |  | W | 2024-10-23 | 58
|  |  |  | Th | 2024-10-24 | 59
|  |  |  | F | 2024-10-25 | 60
|  |  |  | Sa | 2024-10-26 | 61
|  |  |  | Su | 2024-10-27 | 62
|  |  |  | M | 2024-10-28 | 63
|  |  |  | T | 2024-10-29 | 64
|  |  |  | W | 2024-10-30 | 65
|  |  |  | Th | 2024-10-31 | 66
|  |  |  | F | 2024-11-01 | 67
|  |  |  | Sa | 2024-11-02 | 68
|  |  |  | Su | 2024-11-03 | 69
|  |  |  | M | 2024-11-04 | 70
|  |  |  | T | 2024-11-05 | 71
|  |  |  | W | 2024-11-06 | 72
|  |  |  | Th | 2024-11-07 | 73
|  |  |  | F | 2024-11-08 | 74
|  |  |  | Sa | 2024-11-09 | 75
|  |  |  | Su | 2024-11-10 | 76
|  |  |  | M | 2024-11-11 | 77
|  |  |  | T | 2024-11-12 | 78
|  |  |  | W | 2024-11-13 | 79
|  |  |  | Th | 2024-11-14 | 80
|  |  |  | F | 2024-11-15 | 81
|  |  |  | Sa | 2024-11-16 | 82
|  |  |  | Su | 2024-11-17 | 83
|  |  |  | M | 2024-11-18 | 84
|  |  |  | T | 2024-11-19 | 85
|  |  |  | W | 2024-11-20 | 86
|  |  |  | Th | 2024-11-21 | 87
|  |  |  | F | 2024-11-22 | 88
|  |  |  | Sa | 2024-11-23 | 89
|  |  |  | Su | 2024-11-24 | 90
|  |  |  | M | 2024-11-25 | 91
|  |  |  | T | 2024-11-26 | 92
|  |  |  | W | 2024-11-27 | 93
|  |  |  | Th | 2024-11-28 | 94
|  |  |  | F | 2024-11-29 | 95
|  |  |  | Sa | 2024-11-30 | 96
|  |  |  | Su | 2024-12-01 | 97
[5 empty] | 2024-12-02 | 98
[5 empty] | 2024-12-03 | 99
[5 empty] | 2024-12-04 | 100
[5 empty] | 2024-12-05 | 101
[5 empty] | 2024-12-06 | 102
[5 empty] | 2024-12-07 | 103

## ganttChartDays
Task | Days Since Start | Days Left for Completion | Day end | Task | Expected Start Date | Expected End Date | Estimated Date to Complete | 1 | T | 2024-08-27 | Start | End | BackEnd
Team Composition Form | 1 | 3 | 4 | Team Composition Form | 2024-08-27 | 2024-08-30 | 2024-08-29 | 2 | W | 2024-08-28 | 2024-09-16 | 2024-09-30 | Table Design
Project Overview Proposal | 4 | 7 | 11 | Project Overview Proposal | 2024-08-30 | 2024-09-06 | 2024-09-02 | 3 | Th | 2024-08-29 | 2024-09-30 | 2024-10-13 | Crud
Software Development Plan | 11 | 7 | 18 | Software Development Plan | 2024-09-06 | 2024-09-13 | 2024-09-02 | 4 | F | 2024-08-30 | 2024-10-13 | 2024-10-28 | Business Logic
User Story Compendium | 18 | 7 | 25 | User Story Compendium | 2024-09-13 | 2024-09-20 | 2024-09-02 | 5 | Sa | 2024-08-31 | 2024-10-28 | 2024-11-04 | Reports
MVS | 25 | 2 | 27 | MVS | 2024-09-20 | 2024-09-22 | 2024-08-28 | 6 | Su | 2024-09-01 |  |  | Testing
Requirements Specification | 27 | 5 | 32 | Requirements Specification | 2024-09-22 | 2024-09-27 | 2024-08-31 | 7 | M | 2024-09-02 | Start | End | Front End
Wireframe | 27 | 7 | 34 | Wireframe | 2024-09-22 | 2024-09-29 | 2024-09-02 | 8 | T | 2024-09-03 | 2024-09-22 | 2024-09-29 | Wireframes
Table Design | 21 | 14 | 35 | Table Design | 2024-09-16 | 2024-09-30 | 2024-09-09 | 9 | W | 2024-09-04 | 2024-09-29 | 2024-10-06 | UI
Design Specificaition | 32 | 14 | 46 | Design Specificaition | 2024-09-27 | 2024-10-11 | 2024-09-09 | 10 | Th | 2024-09-05 | 2024-10-14 | 2024-10-28 | HTML/CSS
CRUD operations | 35 | 14 | 49 | CRUD operations | 2024-09-30 | 2024-10-14 | 2024-09-09 | 11 | F | 2024-09-06 | 2024-10-28 | 2024-11-04 | Reports
UI Tasks Complete | 34 | 14 | 48 | UI Tasks Complete | 2024-09-29 | 2024-10-13 | 2024-09-09 | 12 | Sa | 2024-09-07 |  |  | Testing
Business Logic / Code complete | 49 | 14 | 63 | Business Logic / Code complete | 2024-10-14 | 2024-10-28 | 2024-09-09 | 13 | Su | 2024-09-08
HTML / CSS - Finailzed | 49 | 14 | 63 | HTML / CSS - Finailzed | 2024-10-14 | 2024-10-28 | 2024-09-09 | 14 | M | 2024-09-09
Reports - integrate for reports | 63 | 7 | 70 | Reports - integrate for reports | 2024-10-28 | 2024-11-04 | 2024-09-02 | 15 | T | 2024-09-10
Additional Features as time allows | 70 | 7 | 77 | Additional Features as time allows | 2024-11-04 | 2024-11-11 | 2024-09-02 | 16 | W | 2024-09-11
Testing / Finalizing | 77 | 14 | 91 | Testing / Finalizing | 2024-11-11 | 2024-11-25 | 2024-09-09 | 17 | Th | 2024-09-12
[8 empty] | 18 | F | 2024-09-13
[8 empty] | 19 | Sa | 2024-09-14
[8 empty] | 20 | Su | 2024-09-15
[8 empty] | 21 | M | 2024-09-16
[8 empty] | 22 | T | 2024-09-17
[8 empty] | 23 | W | 2024-09-18
[8 empty] | 24 | Th | 2024-09-19
[8 empty] | 25 | F | 2024-09-20
[8 empty] | 26 | Sa | 2024-09-21
[8 empty] | 27 | Su | 2024-09-22
[8 empty] | 28 | M | 2024-09-23
[8 empty] | 29 | T | 2024-09-24
[8 empty] | 30 | W | 2024-09-25
[8 empty] | 31 | Th | 2024-09-26
[8 empty] | 32 | F | 2024-09-27
[8 empty] | 33 | Sa | 2024-09-28
[8 empty] | 34 | Su | 2024-09-29
[8 empty] | 35 | M | 2024-09-30
[8 empty] | 36 | T | 2024-10-01
[8 empty] | 37 | W | 2024-10-02
[8 empty] | 38 | Th | 2024-10-03
[8 empty] | 39 | F | 2024-10-04
[8 empty] | 40 | Sa | 2024-10-05
[8 empty] | 41 | Su | 2024-10-06
[8 empty] | 42 | M | 2024-10-07
[8 empty] | 43 | T | 2024-10-08
[8 empty] | 44 | W | 2024-10-09
[8 empty] | 45 | Th | 2024-10-10
[8 empty] | 46 | F | 2024-10-11
[8 empty] | 47 | Sa | 2024-10-12
[8 empty] | 48 | Su | 2024-10-13
[8 empty] | 49 | M | 2024-10-14
[8 empty] | 50 | T | 2024-10-15
[8 empty] | 51 | W | 2024-10-16
[8 empty] | 52 | Th | 2024-10-17
[8 empty] | 53 | F | 2024-10-18
[8 empty] | 54 | Sa | 2024-10-19
[8 empty] | 55 | Su | 2024-10-20
[8 empty] | 56 | M | 2024-10-21
[8 empty] | 57 | T | 2024-10-22
[8 empty] | 58 | W | 2024-10-23
[8 empty] | 59 | Th | 2024-10-24
[8 empty] | 60 | F | 2024-10-25
[8 empty] | 61 | Sa | 2024-10-26
[8 empty] | 62 | Su | 2024-10-27
[8 empty] | 63 | M | 2024-10-28
[8 empty] | 64 | T | 2024-10-29
[8 empty] | 65 | W | 2024-10-30
[8 empty] | 66 | Th | 2024-10-31
[8 empty] | 67 | F | 2024-11-01
[8 empty] | 68 | Sa | 2024-11-02
[8 empty] | 69 | Su | 2024-11-03
[8 empty] | 70 | M | 2024-11-04
[8 empty] | 71 | T | 2024-11-05
[8 empty] | 72 | W | 2024-11-06
[8 empty] | 73 | Th | 2024-11-07
[8 empty] | 74 | F | 2024-11-08
[8 empty] | 75 | Sa | 2024-11-09
[8 empty] | 76 | Su | 2024-11-10
[8 empty] | 77 | M | 2024-11-11
[8 empty] | 78 | T | 2024-11-12
[8 empty] | 79 | W | 2024-11-13
[8 empty] | 80 | Th | 2024-11-14
[8 empty] | 81 | F | 2024-11-15
[8 empty] | 82 | Sa | 2024-11-16
[8 empty] | 83 | Su | 2024-11-17
[8 empty] | 84 | M | 2024-11-18
[8 empty] | 85 | T | 2024-11-19
[8 empty] | 86 | W | 2024-11-20
[8 empty] | 87 | Th | 2024-11-21
[8 empty] | 88 | F | 2024-11-22
[8 empty] | 89 | Sa | 2024-11-23
[8 empty] | 90 | Su | 2024-11-24
[8 empty] | 91 | M | 2024-11-25
[8 empty] | 92 | T | 2024-11-26
[8 empty] | 93 | W | 2024-11-27
[8 empty] | 94 | Th | 2024-11-28
[8 empty] | 95 | F | 2024-11-29
[8 empty] | 96 | Sa | 2024-11-30
[8 empty] | 97 | Su | 2024-12-01
[8 empty] | 98 |  | 2024-12-02
[8 empty] | 99 |  | 2024-12-03
[8 empty] | 100 |  | 2024-12-04
[8 empty] | 101 |  | 2024-12-05
[8 empty] | 102 |  | 2024-12-06
[8 empty] | 103 |  | 2024-12-07
Formulas:
Expected Start Date = VLOOKUP([Days Since Start],$I:$K,3,FALSE)
Expected End Date = VLOOKUP([Day end],$I:$K,3,FALSE)
Estimated Date to Complete = VLOOKUP([Days Left for Completion],$I:$K,3,FALSE)